## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Strain injuries | Working for too long may induce strain injury | Get up and move around every now and again | Maintain a reasonable level of comfort while working | Expected | Minimal | 4 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Loss of Data | Data may be lost throughout the working process | Frequently backup data/be wary where physical copies are stored. | Ensure sensitive data is not lost. | Possible | Severe | 10 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Merge Conflicts | Multiple people working on a branch can cause merge conflicts | Communicate when working on a branch and "git pull" before working | Minimise catastrophic merge conflicts | Possible | Moderate | 6 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Electric Shock | Computers use electricity which could shock the user. | Wear grounding bracelet. | Prevent electric shock. | Unlikely | Minimal | 1 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | Tripping | Very loose exposed cables opposite the stairs could cause injury. | Move cables away from stairs | Prevent grave injury. | Guaranteed | Severe | 25 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Spontaneous sickness | Spontaneous sickness could inhibit project progress. | Frequently produce detailed comments and documentation. | Reduce impact on project velocity. | Expected | Moderate | 12
7 | Disconnection to the internet | Internet connection can cut out for many reasons increasing the reliabilty of local storage | Ensure that all files that I need are also saved locally so I can continue even when offline | Save files locally as well as on github so that I always have access to it to reduce disruption | Possible | Minor | 4
8 | Software issues | Issues involve the programs being used like Eclipse and MySQL not working as intended | I have an alternate intallation on my laptop on standby incase I cannot fix the problems I encounter | To reduce the amount of time spend fixing problems that are not imediately related to the project | Likely | Minor | 6
9 | Hardware issues | Some aspect of the hardware im using can fail causing my PC to stop working | I have a laptop I can use and as long as everything is regularly commited to git hub I can easily transfer the work | To maintain my working environment to reduce time wasted on uneccessary problems | Possible | Minor | 4
10 | Burn out | Working for too long may cause burnout reducing the effectivness of time spent on t he project | Make sure to take regular breaks and not to work too late into the night | Taking time off work every now and again can improve the overall quality of the work in the long run | Possible | Major | 8
11 | Falling behind schedule | Falling behind can either cause the project to not be completed or encourage an unhealthy amount of work increasing the chance of burn out | Ensure that each day has set tasks to be completed and that the schedule is adhered to, allowing for some time for things to go wrong | To maintain a consistent rate of work to help prevent burn out but to also encourage that the project gets completed on time | Possible | Major | 8
12 | Missing knowledge | Not understanding how to progress on a project due to a lack of the required technical skills | The resources to learn are availible especially on the QA community site so time spent leanring isnt wasted | To overcome technical problems as fast as possible using all of the resources availible | Expected | Minor | 10